## PROJECT VISION
PROJECT VISION
PROJECT | Name : | 吾宠
| Vision: | 打造石家庄最大网上人宠互动平台，并在日后扩展到其他城市。
analysis of profit | 充值兑换积分，积分可供用户人宠互动消费
活动推荐广告
Note on D3: Luc Segers: Insert the name of the project
Note on D4: Luc Segers: Insert the descript of the Vision
Note on D7: Luc Segers: Insert the name of the customer
Note on D8: Luc Segers: Insert the name of the supplier

## PROJECT BACKLOG
PROJECT BACKLOG
13 | = highest Reference ID number
引用编号 | 版本 | 冲刺号 | 分类 | 标题 | 故事 | 类型 | 进度 | 初始估计（h） | 优先级 | 如何演示 | 商业价值 | 理想时间（h） | 调整因子 | 复杂度 | 信息度 | 备注
1 | 1 | 1 | user story | 最热宠物动态推荐 | 作为一个偶尔关注宠物动态的铲屎官，我希望能够有一个最热动态推荐，以便于减轻我浏览的困惑。 | Initial Feature | Not Done | 2 | 98 |  |  | 2
2 | 1 | 1 | user story | 手机快速注册 | 作为一个铲屎官，我希望能够通过本机号快速注册，以便于更快捷的登录系统。 | Initial Feature | Not Done | 1 | 96 |  |  | 1
3 | 1 | 1 | user story | QQ登录 | 作为一个铲屎官，我希望能够通过QQ登录，以便于更快捷的登录系统，而省去注册环节。 | Initial Feature | Not Done | 3 | 95 |  |  | 3
4 | 1 | 1 | user story | 微信登录 | 作为一个铲屎官，我希望能够通过微信登录，以便于更快捷的登录系统，而省去注册环节。 | Initial Feature | Not Done | 1 | 93 |  |  | 1
5 | 1 | 1 | user story | 微博登录 | 作为一个铲屎官，我希望能够通过微博登录，以便于更快捷的登录系统，而省去注册环节。 | Initial Feature | Not Done | 1 | 93 |  |  | 2
6 | 1 | 1 | user story | 好友列表 | 作为一个铲屎官，我希望可以维护好友列表，从而可以快速访问他的动态 | Initial Feature | Not Done | 1 | 90 |  |  | 1
7 | 1 | 1 | user story | 找回密码 | 作为一个铲屎官，我希望可以通过找回密码，从而登录成功。 | Initial Feature | Not Done | 2 | 90 |  |  | 2
8 | 1 | 1 | user story | 网银充值 | 作为一个铲屎官，我希望可以通过网银快速充值积分。 | Initial Feature | Not Done | 3 | 88 |  |  | 3
9 | 1 | 1 | user story | 记住密码 | 作为一个铲屎官，我希望能够通过记住密码，以便于快速登录。 | Initial Feature | Not Done | 1 | 85 |  |  | 1
10 | 1 | 1 | user story | 打卡提醒 | 作为一个铲屎官，我希望能够通过打卡提醒，以便于更高效的完成与宠物的互动。 | Initial Feature | Not Done | 2 | 80 |  |  | 2
11 | 1 | 1 | user story | 动态发布 | 作为一个铲屎官，我希望能够通过动态发布，以便于分享自己与宠物的日常。 | Initial Feature | Not Done | 1 | 70 |  |  | 1
Total |  | 11 | [5 empty] | 18
Generate index cards
Note on A4: Luc Segers: This is the highest reference ID number used so far.
Note on A5: Luc Segers: This reference ID should be unique. This number is used throughout the whole worksheet so be aware.
Note on B5: Luc Segers: This is the release where the story will be developped
Note on C5: Luc Segers: This is the sprint where the story will be developped
Note on D5: Luc Segers: This is a category to which the story belongs. Example : Infrastrucuture, Back-End, Animation, ...
Note on F5: Luc Segers: This is the story (Feature, Epic, User). Depending on in which phase you are in (Présales, Scope, …) the detail could be higher. Normally you could describe a user story as follow: As a <Role> I can do <this> and the result is <that> ... Offcourse this is not always possible, so you should be creative. A story should conduct to the following rules: I = Independent N = Negotiable V = Valuable to customer E = Estimatable S = Small T = Testable
Note on G5: Luc Segers: Type of the story.
Note on H5: Luc Segers: Status of the story
Note on I5: Luc Segers: This column is calculated: Ideal Hours * Adjustment Factor
Note on J5: Luc Segers: M = Must Have S = Should Have C = Could Have W = Won't have this time
Note on L5: Luc Segers: 0 = Lowest Business Value 100 = Highest Business Value
Note on M5: Luc Segers: Enter here the new ideal estimates which are done with planningpoker
Note on N5: Luc Segers: This column is calculated based on the values of complexity and information. The data is looked up in the setup tab.
Note on O5: Luc Segers: Complexity 0 = Not Defined 1 = Very Simple 2 = Simple 3 = Moderate 4 = Complex 5 = Extreme Complex
Note on P5: Luc Segers: Information 0 = Not Defined 1 = No information 2 = Little information 3 = Moderate information 4 = Much information 5 = All information
Note on C17: Luc Segers: Total amount of stories available in the project backlog
Note on I17: Luc Segers: total amount of estimated hours